## Sheet1
Task | Description | Start Date | End date | Timeline | Status
Project | CMOWE - A blockchain based online platform for filmmakers and movie lovers built with love | 2021-08-12 | 2021-11-22
Task 1 | Domain research, scope identification | 2021-08-13 | 2021-08-18 |  | Complete
Task 2 | Research on crowdfunding and crowdsourcing techniques | 2021-08-20 | 2021-08-24 |  | Complete
Task 3 | Going through filmmaking processes of various countriues | 2021-08-25 | 2021-08-31 |  | Complete
Task 4 | Identifying the current problems and narrow down of scope | 2021-09-02 | 2021-09-05 |  | Complete
Task 6 | Exploring technology stack for platform building(Figma, Truffle, Ganache, web3js, Solidity, React and Metamask and nodejs, IPFS, Infura API) | 2021-09-07 | 2021-09-14 |  | Complete
Task 7 | Visualizing project vision using FIGMA | 2021-09-15 | 2021-09-22 |  | Complete
Task 8 | Video making and editing for solution proposed and deploying it using Infura API endpoint into IPFS | 2021-09-22 | 2021-09-28 |  | Complete
Task 9 | Getting familiar with deployment of basic Blockchain contracts | 2021-10-01 | 2021-10-15 |  | Complete
Task 10 | Building the backend using necessary smart contracts | 2021-10-17 | 2021-10-24 |  | Complete
Task 11 | Testing of built smart contracts | 2021-10-26 | 2021-11-02 |  | Complete
Task 12 | Building the front end using the REACT library(design of the intended 4 components) | 2021-11-04 | 2021-11-08 |  | Complete
Task 13 | Integrating the front end and backend(smart contracts) using web3js and using the utils folder for configuration | 2021-11-10 | 2021-11-15 |  | Complete
Task 14 | Project testing for all the cases deployed, documentation and report making | 2021-11-17 | 2021-11-20 |  | Complete
Task 15 | Experimantation on test networks such as Rinkeby, Ropsten. | 2021-11-21 | 2021-11-23 |  | Complete